HUMAN SERVICES PLAN IMPLEMENTATION REPORT – COMMUNITY SECTOR

Note: In spite of the initial attention on the alleged failings or oversupply of non-government services, the actual implementation of the reform agenda has required improvements in the performance of mainstream NSW government-provided services. This change in focus has never been publicly acknowledged but is in my view a credit to both the staff of the RWA and the NSW public service. Also, it has taken the heat off community-based services. In this light, the lack of ‘progress’ on forcing small diverse services into larger integrated one-stop-shops is cause for general relief.

| Objective | Who | Progress so far (1st report April 06) | Comments |
| --- | --- | --- | --- |
| Improve health & wellbeing of children | Health DoCs DET RWA+ | Aboriginal health educators at AMS Families first funding application Culturally appropriate childcare 0-5 Connect Redfern 100 affordable childcare places | DoCS reviewed Barnardos, Mudgin-Gal CoS did this I think |
| Lift school numeracy & literacy | DET DAA | Families First Connect Redfern Aboriginal models (HIPPY) ended Dec 06 (also see above families first) | Reporting is politically sensitive and won’t help the self-esteem of Alex Park students. |
| Lift local school attendance and retention | DET DoCS | Student leadership programs ASLOS & HSLOS Yallamundi 1 extra staff Transport taskforce 1 meeting | More recent reports from DET to HSMAC suggest they are getting good results on improving attendance and retention |
| Improve support for vulnerable people | Health DoH Health TAFE DADHC DoCS DAA | Housing and Support (HASI) for tenants with mental illness Joint Guarantee of Service (JGoS) Improve integration of drug and mental health Strengthen rehabilitation programs Improve training and employability Support children with disabilities Case Co-ordination project Respond to Aboriginal community grief loss, Stolen Generation | These are statewide programs not targeted at this area. They have had meetings Liaison re workskills Supported playgroups (Jo Fletcher) Established. (still in operation?) Organising a meeting? –We should follow up |

| Reduce family violence | RWA Police DoCS | Family Violence Taskforce Prevention program men and boys Improve police response Train ACLOs After hours services | Claimed ‘blackout violence’ but didn’t fund it – otherwise good ? Investigating options ? has this happened? Plan of action drafted |
| --- | --- | --- | --- |
| Increase participation of young people in the community | RWA DoCS RWA DSRT & CoS Police RWA Health | Combine youth services into 3 precincts link service integration to funding After hours & holiday programs Consultation & information Positive police relationships Coordinated sport and cultural activities Youth mentoring program Aboriginal mentoring Integrated mental health etc Sexual health Discharge referrals GPs capacity | Not happening. Problem may be lack of venues. Note PCYC planned to move to Redfern School site. Small $ to midnight basketball ? Proposed referral service (privacy?) ? (also NGOs) happening via men’s group? Meetings and research Unclear re sexual assault Directory and care plan ‘being developed’ |
| Increase young peoples’ access to employment & training | DET & TAFE RWA | Vocational education strategy RWA training centre – hospitality Aboriginal employment strategy | Not clear why this was here and not in the employment plan Aboriginal enterprise service |
| Reduce drug & alcohol misuse | Health DET Health | Health promotion Drug & Alcohol Taskforce Aboriginal education Culturally appropriate detox & rehab Community health facility | No funding found Street drinking/alcohol free zones ‘working’ on drinking on Waterloo Green consultation & review discussing… (not happening) planned for courthouse site. |

| Reduce offending & recidivism | AGD & DAA DJJ DJJ DAA CoS | Circle sentencing & community justice group Youth cautioning Parole/post-release support Post release accommodation & support for women Community Safety Plan | No circle (why?) Justice group - funded 3 yrs at RLC cancelled after 1 year. Dependent on justice group (so not happening?) maybe via ACLOs and YCLOs. Funds SSYS for this.(ongoing?) Meeting, assessing, drafting… nothing Good for a while. Task force no longer active. CoS now focussing on other suburbs. |
| --- | --- | --- | --- |
| Build community capacity | RWA CoS DET RWA & DAA DoH RWA RWA CRC & DAA | Develop partnerships, networks, foster community participation, improved communication & training Redfern Street Festival ‘sticky-beak’ tours Web portal for NGOs Redfern-Waterloo Information Centre Cultural history project Small community events Locate services on estates Build partnerships Aboriginal community Capacity training Aboriginal organisations Public/private partnerships – food co-op Cross-cultural training package | !!!!!!!!!!!!!!!! ? Why DET? Two powerpoint events put on by RWA. Not sticky-beak tours although they used the name. Not happening. Not happening Not happening $200 grants. DAA making a list. Not happening. DoH say they already do. “under way” !!! some training offered. May be inappropriate Not a success ? |

| Implementation & reform | RWA RWA | Implementation Senior Officers Group HSMAC “a reference point for community participation and client feedback.” Pilot shared back office for NGOs to make us ‘more efficient’ Streamline compliance costs for NGOs. Enhance NGO capacity to use IT Standardise and streamline client intake & referral Review after 18 months Encourage corporate citizenship, establish $$ trust with ‘clear set of guiding principles’ | In action. !!! (bit hard when all is ‘cabinet –in-confidence’) Not happening. I’d like to see that… Ditto .. (privacy, anyone?) baseline data not yet established I think this went to ‘Sydney Community Trust’. Rumoured not to have clear principles. Anyone tried to apply? |
| --- | --- | --- | --- |