WATERLOO GREEN ACTION PLAN

REPORT CARD AS AT JUNE 2008

Legend

 denotes Action completed

 denotes Action has commenced and is in progress

LA – Lead Agency

SA – Support Agency

Acronyms

CoS		City of Sydney

DoCS		NSW Department of Community Services

DADHC		NSW Department of Ageing, Disability and Home Care

HCAP		Housing Communities Assistance Program

HNSW		Housing NSW

ICHOSS		Inner City Homelessness Outreach Support Service

MoT		Ministry of Transport

NGO		Non Government Organisation

RWA		Redfern Waterloo Authority

Strategy 1: Improve Public Safety and Amenity on and around Waterloo Green

| Action | Agency report | Community comment June 2008 |
| --- | --- | --- |
| Implement the recommendations of the Waterloo Green Safety Audit including timely and responsive maintenance in and around public spaces and timely graffiti removal (Agencies identified through Audit) |  |  |
| Audit current security, lighting and other maintenance programs that impact on personal safety (LA:HNSW) (SA: CoS) | - Lighting Audit completed. - Maintenance and repair program continues on an ongoing basis. - Upgrading of external lighting on Waterloo Green; adjacent undercover car parks & common area lighting inside Turanga commenced on 07.05.08 | - Happy with work that has commenced - Will the other side of Waterloo Green will i.e.: area in front of Banks/Cook completed also? - The light work is an essential part and should make a huge difference. |
| Test the effectiveness of “this graffiti has been reported and police are investigating” sticker-type signs in a three month trial from October to December 2007. (LA: Police) (SA: HNSW, Residents) | - Selection of building for trial - Police and Housing have established clear roles and responsibilities - Stickers have been printed - Trial commenced end of February 2008 - Partner agencies held progress reviews on 1.4.08 & 7.5.08 - Feedback was sought from residents at the Marton precinct meeting on 22 April 2008 | - Concerns were raised about length of time for implementation and review. - Will the review highlight any detection rates as result of increased reporting? - If programme proves to be successful will this be rolled out across the estate? - Noted the success of the Community mosaic project further funding for similar projects being pursed by Factory/ HCAP - Residents highlighted their own efforts of paint out projects of their own initiative should be explored as part of the review and resourced. |
| Explore opportunities for local youth and residents to participate in cultural painting of walls and fire stairs in nearby high rise buildings and other common graffiti “hot spots” (LA: HNSW) (SA: NGO’s, CoS) |  | Factory / HCAP community Mosaic project was successful should be extended to other areas |
| Hold meetings with residents in October 2007 to plan training opportunities in gardening, landscaping and facilities management of other areas of resident interest. (LA:TAFE Outreach/HNSW) (SA: Residents, CoS) | - This action is reliant upon the completion of the Landscape Design Plan as this will focus the type of training. - The Department of Commerce has been engaged to develop a landscape plan for Waterloo Green. Community and stakeholder consultations have commenced. | Is there interim activity courses that could be ruin within community rooms? Factory has recruited a part time manager for the Waterloo Recycling workshop to re activate this project. Comment on Landscape were in the main positive and recorded by Dept of Commerce; consultations on going. |
| Deliver agreed training opportunities throughout 2008( LA: TAFE Outreach/HNSW) (SA: Residents, CoS | - See above |  |

Strategy 2: Reduce Anti-Social Behaviour associated with excessive public drinking

| Action | Agency report | Community comment |
| --- | --- | --- |
| Investigate opportunities for police community liaison officers to work more closely with residents (LA: Police with HNSW & residents) | - Police pushbike patrols in place - Crime Prevention Officer meets regularly with residents and local HNSW staff | Happy that Waterloo green action group will expand to become Waterloo wide safety action group as part of the Waterloo NAB news strategy. Discussions/ implementation on going. |
| Improve reporting of anti-social behaviour on Waterloo Estate by residents(LA: Police with HNSW & residents) | - HNSW continually encourages residents to report anti-social behaviour to NSW Police. This is reinforced at Housing Standards, precinct and community meetings | Community noted improvement to new housing standards format. Means to promote anonymous reporting through Crime stoppers or other mechanism etc should be explored. |
| Encourage reporting of graffiti by HNSW staff and residents to the 131 444 Police Assistance Line. (LA: HNSW) | - As above |  |
| Investigate opportunities to enhance policing responses through: - Regular meetings between Community Policing Officers, HNSW, community safety meetings and feedback from residents at community BBQ’s and similar events (LA: Police). - Community Policing Officers providing more information about Waterloo Estate to General Duties police (LA:Police & HNSW) - Ongoing development by the Department of Housing and Redfern Police of responses to anti-social behaviour (LA:Police & HNSW) | - Staff at both agencies liaise regularly, both formally and informally in regard to issues. - Last meeting between senior RLAC & HNSW staff was 26.05.08. Next meeting 2.7.08. | Residents happy with level of attendance of crime prevention officer at residents based meetings, should be built upon through the new action group recommendation of the Waterloo NAB. Concerns raised about liquor licensing particular early morning and late night premises |
| Through the existing Liquor Accord, continue to promote responsible service of alcohol in pubs and other outlets. (LA: NSW Liquor Accord Partners) | - Police have requested Liquor Accord to consider solutions/options to replace sales of bottled beer. | Concerns raised about liquor licensing particular early morning and late night premises |
| Investigate other community based interventions which can reduce excessive drinking on public open space on Waterloo Green (LA:HNSW, NSW Health, Police, CoS, RWA, NGO’s) | - Initial planning meeting held with government and NGO’s on 8 February. 30 participants involved. A range of potential solutions suggested. - Potential solutions being investigated by the RWA, HCAP, Police and Housing. - Next meeting of the working group to be scheduled (TBA) to report back on viability of proposed solutions and to action solutions where appropriate. - Planning meeting held to establish Community Drug Action Team with RWA, Police and Health 13 February 2008. - CDAT meetings held 8.03.08, 4.04.08, 19.05.08. Next meeting 06.06.08. - Community Action Support Group formed comprising of ICHOSS, Missionbeat, AMS, and Police. This group have actively engaged with the drinkers on WG several times. - RWA funded CAST BBQ including HNSW and Centrelink held on 14.05.08. Over 40 people involved. - Application to City of Sydney Quick Response Grants for funding of BBQ Program submitted. - Applications for funding of P/T Short Term Link Worker and Community events submitted to NSW Health for funding under the Risky Drinking Project. - Confirmation from NSW Health funding approved. | High levels of street drinking remain a concern, community anticipate that it may increase again over summer months. Legal advice received says Department of Housing can make the land Alcohol Free but may be problematic to enforce. Clear statement of intent should be made on this issue. Community happy to see service engaged with both victims and perpetrators of issues. |
| Investigate scope for ICHOSS and Missionbeat to work on Waterloo Green (LA:Police) (SA: CoS, NSW Health) | - ICHOSS and Missionbeat participated in the community based interventions planning meetings. - ICHOSS and Missionbeat committed to CDAT membership. - ICHOSS and Missionbeat are the lead agencies on the CAST Project – see above | Missionbeat has been seen engaging with street drinker regularly with positive effect. Please retain high presence level. |
| Investigate funding opportunities for a Waterloo Estate drug and alcohol health promotion campaign (NSW Health) (SA: HNSW, RWA) | - CDAT to consider as part of the 2008/09 Action plan to be developed at the 06.06.08 meeting. |  |

Strategy 3: Improve information to residents about services

| Action | Agency report | Community comment |
| --- | --- | --- |
| Develop a services and events guide for Waterloo Estate residents (LA:HNSW in consultation with other Human Services agencies and NGO) | - CDAT to consider as part of the 2008/09 Action plan to be developed at the 06.06.08 meeting. | Residents highlighted the lack of funding for RedWaternews production may make the objective difficult to achieve. |

]

Strategy 4: Improve access to key human services

| Action | Agency report | Community comment |
| --- | --- | --- |
| Improve effectiveness of home visiting and other in-home supports, especially for clients with complex needs. (LA:DADHC, DoCS, Health, MoT) (SA: HNSW) |  | Why has there been a decrease in agencies attending the Action group meeting to report back on such issues from both frontline and senior staff. Will be flagged at ISOG and HSMAC. |
| Human Services to ensure local HNSW staff and NGO’s working closely with residents are aware of available health services and how they can refer residents to these services ( LA: Government and NGO’s human service providers) | - HNSW Client services staff have been briefed on services including RICHSS, HASI II, Centacare, Connect Redfern, Mercy Arms |  |
| Government Human Services agencies will participate in resident’s information days and other events to promote services to residents and encourage non-Government service providers to do likewise. (LA: Government agencies) | - HNSW Client services staff have been briefed on services including RICHHS, HASI II, Centacare, Connect Redfern, Mercy Arms |  |
| Redfern Waterloo Human Services working parties led by NSW Health to consider access and service delivery needs of Waterloo Estate residents. (LA: NSW Health) |  |  |
| Consult with Central Sydney Division of General Practice and local GP’s about barriers to access to health service for Waterloo Green estate residents. (LA: NSW Health) | - Central Sydney Division of GP’s participated in the community interventions to reduce excessive drinking planning meeting 8 Feb. |  |
| HNSW to ensure that key human service agencies are advised of community events held on Waterloo Green (HNSW) | - Use of existing networks & email - Related also to 3 |  |
| Enhance early childhood support services on Waterloo Green (LA: DoCS) (SA: HNSW, NGO’s, NSW Health) | - The Redfern Early Child Health Centre has relocated to HNSW premises at 4/95 Wellington St, Waterloo which is in close proximity to the estate (Health) | Relocation of service although welcomed as closer location however does not imply enhanced service, therefore action item should remain. |

Strategy 5: Encourage greater use of Waterloo Estate meeting and activities spaces.

| Action | Agency report | Community comment |
| --- | --- | --- |
| Agencies to liaise with Dept of Housing regarding opportunities to use meeting spaces and other facilities on Waterloo estate (LA:Government and NGO’s) | - Barnados operate Kidspeak on Waterloo Green every Friday afternoon. - RICHSS utilising Turanga community room “Sit for Fit” | Looking forward to the reactivation of community rooms. |
| Review current usage levels of meeting rooms and other community facilities on Waterloo Estate (LA:HNSW) | - HNSW has completed an inspection of the community rooms. Minor maintenance issues identified. - A centralised booking system with application form & terms & conditions of use is being developed. Precinct representatives have been involved in the discussions including meeting with the Business Manager Insurance. |  |
| Government human service agencies will hold more activities in the Waterloo Green area and will encourage non-government service providers to do the same. (Government agencies) | - CAST program BBQ’s in place. | Reactivation of Recycling workshop by summer 2008- Factory will be hosting its second Christmas Summer on the Green event after last year’s success. HCAP facilitating planning. |
| Encourage more use of open spaces and the basketball court for activities for younger people (LA:HNSW, HCAP, Youth Services, Dept Sport & Rec) | See 1.5 |  |
| Encourage culturally-specific community groups to make more use of meeting and other spaces (LA:All Human services agencies, NGO’s in partnership with HNSW) | See 5.2 |  |

Strategy 6: Increase interaction between older residents and young people

| Action | Agency report | Community comment |
| --- | --- | --- |
| Identify opportunities for more positive interactions between residents and local youth (RWA, Dept Sport & Recreation, local schools) |  |  |

Strategy 7: Monitor implementation

| Action | Agency report | Community comment |
| --- | --- | --- |
| All agencies to report back to each Redfern Human Services Plan Seniors Officers group meeting on progress undertaken to implement the Action Plan (LA:Government agencies) | - Report back 18 December 2007 - Report back 13 February 2008 - Report back 14 March 2008 - Report back 10 April 2008. - Next meeting 12 June 2008 |  |
| HNSW to use human services agency progress reports to provide feedback to local community on implementation of the Action Plan. (LA:Government agencies) | - HNSW & RWA report back to WG Action Group 14 September 2007 - DADHC & RWA brief Eastern Suburbs HACC Forum 21 November 2007 - HNSW, Police and RWA report back to WG Action Group 14 February 2008. - Report back to PACT meeting 15 May 2008. |  |